## Launch Checklist
🚀 SERVE BY EXAMPLE — PRE-LAUNCH MASTER CHECKLIST
50 Must-Do Tasks Before & After Going Live ¦ Built for Founders by Founders
# | DONE? | CATEGORY | TASK | HOW TO DO IT — FOUNDER'S GUIDE | PRIORITY | NOTES | STATUS
1 | ☐ | Legal & Compliance | Register your business entity | If not already done, register as a Pty Ltd (Australia) via ASIC at asic.gov.au. Cost ~$538. Choose a name that matches your brand. You'll need an ACN and ABN. Use a company address (can be home). This protects personal assets and is required for Stripe business accounts. | 🔴 Critical | Cannot verify from code — confirm with ASIC | TODO
2 | ✓ | Legal & Compliance | Get an ABN & register for GST | Apply free at abr.gov.au. If turnover will exceed $75k/yr, register for GST immediately. Once registered, add GST to all Australian sales and lodge BAS quarterly. Update your Stripe tax settings to collect GST automatically. | 🔴 Critical | Confirmed | DONE
3 | ✓ | Legal & Compliance | Publish a Privacy Policy | Use a generator like Termly or Iubenda, or hire a lawyer. Must cover: what data you collect, how you use it, third parties (Stripe, Cloudflare, AI providers), user rights under the Australian Privacy Act. Host at /privacy and link in footer. | 🔴 Critical | Confirmed — /privacy page live | DONE
4 | ✓ | Legal & Compliance | Publish Terms & Conditions | Draft T&Cs covering: acceptable use, subscription terms, cancellation/refund policy, IP ownership of content generated, limitation of liability, governing law (your state, Australia). Link prominently in footer and require acceptance at signup. | 🔴 Critical | Worth a re-read for AI/SaaS gaps | DONE
5 | ☐ | Legal & Compliance | Add a Cookie Consent Banner | Install a GDPR/Australian Privacy Act compliant cookie banner (try CookieYes — free tier available). Categorise cookies: strictly necessary, analytics, marketing. Block non-essential cookies until consent given. Required for EU visitors and best practice globally. | 🟠 High | No cookie banner found in codebase | TODO
6 | ✓ | Legal & Compliance | Create a Refund Policy | Clearly state your refund terms for SaaS: e.g. 14-day money-back guarantee, no refunds after X days, how to request. Publish at /refunds. Under Australian Consumer Law, you must provide remedies for services not fit for purpose. | 🟠 High | Refund terms in T&Cs + pricing FAQ | DONE
7 | ✓ | Legal & Compliance | Review AI-specific liability clauses | Add a clause to your T&Cs limiting liability for AI-generated outputs. State clearly that AI recommendations are not professional advice (legal, financial, HR etc). Specify that users are responsible for verifying AI outputs before acting on them. | 🟠 High | AI liability clause in T&Cs | DONE
8 | ✓ | Security | Enable HTTPS everywhere via Cloudflare | In Cloudflare dashboard → SSL/TLS → set to 'Full (Strict)'. Enable 'Always Use HTTPS'. Turn on HSTS under Edge Certificates. This ensures all traffic is encrypted. You already have Cloudflare — just verify these settings are active. | 🔴 Critical | Confirmed | DONE
9 | ✓ | Security | Set up Cloudflare WAF rules | In Cloudflare → Security → WAF, enable the free managed ruleset. Add rate-limiting rules: e.g. max 10 login attempts per minute per IP. Block known bad bots under Bot Fight Mode. This protects your AI platform from scrapers and brute force. | 🔴 Critical | Worth re-checking WAF rules | DONE
10 | ☐ | Security | Enable 2FA on all admin accounts | Turn on 2-factor authentication for: your domain registrar, Cloudflare, Stripe, hosting provider, email provider, and any database/backend services. Use an authenticator app (Google Authenticator or Authy) rather than SMS. Critical — one compromised account can sink the business. | 🔴 Critical | No 2FA evidence found — do this now | TODO
11 | ✓ | Security | Conduct a basic penetration test | Use free tools: run your URL through OWASP ZAP (free, open source), or use Mozilla Observatory (observatory.mozilla.org). Check for: exposed API keys, SQL injection vectors, XSS vulnerabilities. Fix any HIGH severity findings before launch. | 🔴 Critical | A+ score confirmed | DONE
12 | ✓ | Security | Secure all API keys and secrets | Never commit API keys to GitHub. Use environment variables stored in your hosting provider's secrets manager. Audit your codebase with tools like GitGuardian (free tier). Rotate any keys that may have been exposed. | 🔴 Critical | All secrets in env vars — never hardcoded | DONE
13 | ☐ | Security | Set up automated backups | Configure automated daily backups of your database and file storage. Most cloud providers offer this natively. Test the restore process — a backup you've never tested is not a backup. Store backups in a different region. | 🟠 High | No backup config found in codebase | TODO
14 | ☐ | Payments & Finance | Test Stripe in live mode end-to-end | Use a real card to make a test purchase. Confirm: payment succeeds, receipt email sends, subscription created in Stripe dashboard, webhook fires correctly, user account upgrades in your system. Then refund the test charge. | 🔴 Critical | Marked ?? — needs a real live-mode test run | TODO
15 | ✓ | Payments & Finance | Configure Stripe tax collection | In Stripe Dashboard → Tax, enable automatic tax calculation. Add your business address and tax registration number. Stripe will calculate GST for Australian customers and applicable taxes internationally. This saves you significant accounting headaches. | 🔴 Critical | Confirmed | DONE
16 | ☐ | Payments & Finance | Set up Stripe customer portal | Enable Stripe's built-in customer portal (Dashboard → Settings → Billing → Customer portal). Allow customers to: view invoices, update payment methods, cancel subscriptions. Link to this from your user dashboard. Saves you support tickets. | 🟠 High | API route exists (app/api/billing/portal/route.ts) but NOT linked from UI | IN PROGRESS
17 | ✓ | Payments & Finance | Set up a business bank account | Already done per your notes — great! Ensure the account name matches your registered business name exactly. Set up automatic Stripe payouts to this account. Keep business and personal finances strictly separate for tax purposes. | ✅ Done | Confirmed | DONE
18 | ☐ | Payments & Finance | Create a bookkeeping system | Sign up for Xero or QuickBooks (both have free trials). Connect your business bank account and Stripe. Categorise expenses from day one — this makes tax time much easier. Engage an accountant for your first BAS lodgement. | 🟠 High | No Xero/QuickBooks found | TODO
19 | ✓ | Payments & Finance | Define your pricing tiers clearly | Audit your pricing page. Ensure each tier clearly shows: what's included, monthly vs annual price, any usage limits, and a clear CTA. Add an FAQ answering common pricing questions. Consider a free trial or freemium tier to reduce signup friction. | 🟠 High | Pricing page live with all tiers | DONE
20 | ✓ | Monitoring & Analytics | Install Google Analytics 4 | Create a GA4 property at analytics.google.com. Install the tracking code via Google Tag Manager. Set up key events: signups, subscription starts, feature usage. Configure goals/conversions. This data is invaluable for product decisions. | 🔴 Critical | GA4 tag G-EF9YRFXKBG confirmed in app/layout.tsx | DONE | 2. Code to inject: ```html <script async src="[https://www.googletagmanager.com/gtag/js?id=G-EF9YRFXKBG](https://www.googletagmanager.com/gtag/js?id=G-EF9YRFXKBG)"></script> <script> window.dataLayer = window.dataLayer ¦¦ []; function gtag(){dataLayer.push(arguments);} gtag('js', new Date()); gtag('config', 'G-EF9YRFXKBG'); </script>
21 | ☐ | Monitoring & Analytics | Set up uptime monitoring | Register at UptimeRobot (free tier monitors every 5 min) or Better Uptime. Add your homepage and critical API endpoints. Set alerts to your email and phone. Know before your customers do when something breaks. | 🔴 Critical | No uptime monitoring configured | TODO
22 | ☐ | Monitoring & Analytics | Configure error tracking | Install Sentry (sentry.io — free tier available) in your frontend and backend. It captures JavaScript errors, API failures, and performance issues with full stack traces. Set up Slack or email alerts for new errors. Essential for a technical product. | 🔴 Critical | No Sentry or error tracking found | TODO
23 | ☐ | Monitoring & Analytics | Set up a status page | Create a public status page at Instatus or Statuspage.io (both have free tiers). Link it from your footer and error pages. When you have incidents, communicate proactively. Customers trust transparent companies more. | 🟡 Medium | No status page found | TODO
24 | ☐ | Monitoring & Analytics | Enable Cloudflare Analytics | In Cloudflare dashboard, review Web Analytics and Security Analytics. These give you traffic data without cookies (privacy-friendly). Check for unusual traffic spikes that could indicate bot attacks or viral growth. | 🟡 Medium | Cloudflare Analytics — confirm if paid tier needed | IN PROGRESS
25 | ✓ | SEO & Content | Submit sitemap to Google Search Console | Create an XML sitemap (most frameworks generate this automatically or use a plugin). Submit it at search.google.com/search-console. Verify domain ownership via Cloudflare DNS record. Monitor for crawl errors and indexing issues. | 🔴 Critical | app/sitemap.ts exists + robots.txt points to it — confirm GSC submission | DONE
26 | ☐ | SEO & Content | Optimise meta titles and descriptions | Every page needs a unique meta title (50-60 chars) and description (150-160 chars) containing your target keywords. For 'Serve By Example', target terms like 'bartender training platform', 'hospitality AI training'. Use a tool like Screaming Frog to audit. | 🟠 High | OG tags done. Full per-page title/desc audit still needed | IN PROGRESS
27 | ✓ | SEO & Content | Set up Google Business Profile | Create a free profile at business.google.com. Add your business name, category (Software Company / Education), website, contact details, and description. This helps local SEO and builds credibility. Add photos of your product/team. | 🟠 High | 99% done per notes | DONE
28 | ✓ | SEO & Content | Implement Open Graph tags | Add Open Graph meta tags to all pages so links shared on LinkedIn, Facebook, and Slack show a rich preview with your image and description. Include og:title, og:description, og:image (1200x630px), og:url. Test with Facebook's Sharing Debugger. | 🟠 High | Full OG + Twitter card tags confirmed in layout.tsx | DONE
29 | ☐ | SEO & Content | Build initial backlink profile | Reach out to: hospitality industry blogs, bar association websites, and local business directories for a link to your site. Submit to SaaS directories: Product Hunt, Capterra, G2. Each quality backlink improves your Google ranking. | 🟡 Medium | No backlinks built yet | TODO
30 | ☐ | Customer Experience | Build an onboarding email sequence | Use Mailchimp, ConvertKit or your ESP to create a 5-email onboarding sequence: (1) Welcome + how to start, (2) Key feature spotlight, (3) Success story/case study, (4) Tips for power users, (5) Check-in + offer help. Triggered on signup. | 🔴 Critical | No email automation/sequence found | TODO
31 | ☐ | Customer Experience | Install a live chat widget | Add Intercom, Crisp, or Tidio (free tiers available) to your site. Even if you can't be live 24/7, set up a chatbot to capture leads and answer FAQs. Respond to chats within 1 business hour during launch. Converts visitors to customers. | 🟠 High | No live chat widget in codebase | TODO
32 | ☐ | Customer Experience | Create a knowledge base / help centre | Set up a free help centre using Intercom, Notion (public), or HelpScout Docs. Document: how to get started, common workflows, troubleshooting, FAQ. Link from your product and support channels. Reduces support volume by 30-40%. | 🟠 High | No help centre / Notion docs found | TODO
33 | ☐ | Customer Experience | Define your support SLA | Decide and document your response time commitments: e.g. 'We respond to all queries within 24 hours on business days.' Publish this. Set up a support@ email address. Use a free help desk like Freshdesk if volume grows. | 🟡 Medium | No SLA defined | TODO
34 | ☐ | Customer Experience | Collect and showcase testimonials | Email your beta users asking for a 2-sentence testimonial about their experience. Add these to your homepage and pricing page with their name, venue/bar name, and photo if possible. Social proof is one of the highest-converting elements on a SaaS site. | 🟠 High | Not at beta testing stage yet | TODO
35 | ☐ | Marketing & Growth | Set up LinkedIn company page | Create a LinkedIn company page for Serve By Example. Post 3x per week: product updates, industry insights, customer stories. Hospitality managers and venue owners are active on LinkedIn. This is your #1 B2B channel. | 🟠 High | LinkedIn page setup — not primary focus yet | IN PROGRESS
36 | ☐ | Marketing & Growth | Set up Instagram/TikTok presence | Create accounts for the visual side of your brand. Behind-the-scenes of product development, bartender tips, customer success clips. Short-form video of bartenders using your platform performs extremely well. Consistency beats perfection. | 🟡 Medium | @servebyexample Instagram setup | IN PROGRESS
37 | ☐ | Marketing & Growth | Launch on Product Hunt | Prepare your Product Hunt launch: write a compelling tagline, create a 60-second demo GIF/video, get 20+ upvote commitments from your network before launch day. Launch on a Tuesday-Thursday. A top-5 finish drives significant signups. | 🟠 High | Critical — Product Hunt launch pending | TODO
38 | ☐ | Marketing & Growth | Build a referral program | Add a 'Refer a Friend' feature: give both parties 1 month free or a discount when a referral converts. Tools like ReferralHero or Rewardful integrate with Stripe. Word-of-mouth in tight-knit hospitality communities is extremely powerful. | 🟡 Medium | No referral program built | TODO
39 | ✓ | Marketing & Growth | Create a lead magnet | Build a free resource your target customer desperately wants: e.g. 'The Ultimate Bartender Training Checklist' or '50 Cocktail Recipes Every Bar Should Know'. Offer it in exchange for an email address. Grows your list passively. | 🟡 Medium | SOP Toolkit lead magnet live at /resources/sop-toolkit | DONE
40 | ☐ | Marketing & Growth | Set up email marketing list | Create a Mailchimp or ConvertKit account. Add signup forms to your website. Segment your list: prospects, free users, paid customers. Plan a monthly newsletter with industry news + product updates. Your email list is an asset you own — unlike social media followers. | 🟠 High | No email list / Mailchimp / ConvertKit found | TODO
41 | ✓ | Product & Tech | Create a product roadmap (public or internal) | Document your next 3-6 months of planned features. A public roadmap (use Trello, Notion, or Canny.io) shows prospects you're actively building and builds trust. Let customers upvote features — this also validates what to build next. | 🟡 Medium | Public /roadmap page live | DONE
42 | ☐ | Product & Tech | Set up a user feedback loop | Add a simple NPS survey after 30 days of use (use Delighted or Typeform — free tiers). Ask 'How likely are you to recommend us? Why?' Detractors tell you what's broken. Promoters tell you what's working. Review monthly. | 🟠 High | No NPS/feedback tool installed | TODO
43 | ☐ | Product & Tech | Implement feature flags | Use a tool like LaunchDarkly or a simple database toggle to control feature rollouts. This lets you turn features on/off without a deploy, A/B test new features with a % of users, and quickly disable something that's broken. | 🟡 Medium | No feature flags implemented | TODO
44 | ☐ | Product & Tech | Document your API (if applicable) | If venues or third parties will integrate with your platform, create clear API documentation. Use Swagger/OpenAPI or a tool like Readme.io. Good docs reduce integration support and open B2B partnership opportunities. | 🟡 Medium | No API docs — low priority unless partners needed | TODO
45 | ☐ | Product & Tech | Mobile responsiveness audit | Open your site on an iPhone and Android device. Test every key flow: signup, onboarding, using the AI platform, payment. Many hospitality workers access tools on mobile during their shift. Fix any layout or usability issues immediately. | 🔴 Critical | Mobile-first viewport set but no formal audit done | TODO
46 | ✓ | Product & Tech | Page speed optimisation | Run your site through Google PageSpeed Insights (pagespeed.web.dev). Aim for 90+ on mobile and desktop. Key wins: compress images (use WebP format), enable Cloudflare caching, defer non-critical JavaScript. Speed directly affects SEO and conversion. | 🟠 High | next/image used throughout, Cloudflare CDN | DONE
47 | ☐ | Business Operations | Create a founder investor update template | Even if you're self-funded, practice writing monthly updates: MRR, user growth, top wins, top challenges, what you need help with. Share with mentors/advisors. This discipline keeps you accountable and prepares you for future fundraising. | 🟡 Medium | No investor update template | TODO
48 | ☐ | Business Operations | Set KPIs for the first 90 days | Define 3-5 measurable goals for your first 90 days live: e.g. 50 paying customers, $5k MRR, NPS > 40, churn < 5%. Write them down. Review weekly. These focus your energy and help you know if you're on track or need to pivot. | 🔴 Critical | No 90-day KPIs defined | TODO
49 | ☐ | Business Operations | Build a competitors analysis | Research 5-10 competitors: what they charge, their features, their reviews (G2, Capterra), their marketing channels. Identify your genuine differentiator. Update this document every quarter. Knowing your market makes every product and sales decision smarter. | 🟡 Medium | 2–3 competitors analysed | IN PROGRESS
50 | ☐ | Business Operations | Plan your first 10 customer outreach | Identify 10 dream venues or bars. Find the decision maker on LinkedIn. Send a personalised 3-sentence cold outreach: (1) specific compliment about their venue, (2) one-line value prop, (3) simple ask. Aim for a 15-minute call. Personal outreach > advertising at this stage. | 🔴 Critical | No outreach started | TODO
PRIORITY LEGEND: 🔴 Critical = Do Before or Immediately After Launch ¦ 🟠 High = Within First 2 Weeks ¦ 🟡 Medium = First 30 Days ¦ ✅ Done = Already Completed